## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | Z-4-5 | As a developer, I want to set up the Python environment and install required libraries for contract analysis | MUST HAVE | None | Shradha Naik | 3-Completed
S1 | S1 | Z-4-5 | As a developer, I want to integrate Groq LLM API to enable AI-based compliance analysis | MUST HAVE | Groq API | Shradha Naik | 3-Completed
S1 | S1 | Z-4-5 | As a system, I want to build an initial AI chatbot to answer compliance-related questions | MUST HAVE | Groq API | Shradha Naik | 3-Completed
S1 | S1 | Z-4-5 | As a developer, I want to extract text from uploaded contract PDFs | MUST HAVE | PDF Utils | Shradha Naik | 3-Completed
S2 | S2 | Z-4-5 | As a user, I want to upload a contract and receive GDPR/DPDPA compliance analysis | MUST HAVE | Regulatory Dataset | Shradha Naik | 3-Completed
S2 | S2 | Z-4-5 | As a system, I want to extract important legal clauses from contracts | MUST HAVE | Clause Extractor | Shradha Naik | 3-Completed
S3 | S3 | Z-4-5 | As a system, I want to assess compliance risk based on regulatory updates | MUST HAVE | Risk Engine | Shradha Naik | 3-Completed
S3 | S3 | Z-4-5 | As a system, I want to track regulatory updates and identify impacted contracts | SHOULD HAVE | Regulation Tracker | Shradha Naik | 3-Completed
S4 | S4 | Z-4-5 | As a system, I want to auto-generate revised contracts when regulations change | MUST HAVE | Amendment Engine | Shradha Naik | 3-Completed
S4 | S4 | Z-4-5 | As a user, I want to receive email alerts when contracts are updated | SHOULD HAVE | SMTP Setup | Shradha Naik | 3-Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 58 | 7 | 11 | 12 | 11 | 9 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Z-4-5 | T1-01 | Setup Python virtual environment and install dependencies | 2025-10-16 | 2025-10-17 | Shradha Naik | Build | 3-Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T1-02 | Integrate Groq API and test LLM responses | 2025-10-18 | 2025-10-20 | Shradha Naik | Coding | 3-Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T1-03 | Build initial compliance chatbot using LLM | 2025-10-21 | 2025-10-23 | Shradha Naik | Coding | 3-Completed | 4 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T1-04 | Implement PDF text extraction for contracts | 2025-10-24 | 2025-10-26 | Shradha Naik | Coding | 3-Completed | 4 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
Z-4-5 | T2-01 | Load GDPR and DPDPA regulatory datasets | 2025-11-05 | 2025-11-06 | Shradha Naik | Coding | 3-Completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T2-02 | Extract legal clauses from contracts | 2025-11-07 | 2025-11-09 | Shradha Naik | Coding | 3-Completed | 4 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T2-03 | Perform compliance and risk analysis | 2025-11-10 | 2025-11-12 | Shradha Naik | Coding | 3-Completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
Z-4-5 | T3-01 | Track latest regulatory updates | 2025-11-13 | 2025-11-19 | Shradha Naik | Coding | 3-Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T3-02 | Map regulations to impacted contracts | 2025-11-20 | 2025-11-21 | Shradha Naik | Coding | 3-Completed | 4 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T3-03 | Auto-update contracts based on new rules | 2025-11-22 | 2025-11-26 | Shradha Naik | Coding | 3-Completed | 6 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
Z-4-5 | T4-01 | Implement email alerts using SMTP | 2025-11-27 | 2025-11-30 | Shradha Naik | Integration | 3-Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T4-02 | Improve chatbot accuracy using RAG and embeddings | 2025-12-01 | 2025-12-06 | Shradha Naik | Optimization | 3-Completed | 6 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T4-03 | Final UI integration and system testing | 2025-12-07 | 2025-12-10 | Shradha Naik | Testing | 3-Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 4 | Difficulty in defining chatbot response scope | Refined chatbot prompt and limited compliance domain
Sprint 1 | Day 6 | Inconsistent LLM responses | Tuned system prompts and temperature settings
Sprint 2 | Day 12 | Confusion in compliance report structure | Finalized report format with mentor
Sprint 3 | Day 25 | Challenges in regulatory update simulation | Implemented JSON-based regulation updates
Sprint 4 | Day 42 | Chatbot context loss on long queries | Integrated embedding-based retrieval

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-10-16 | 2025-11-04 | Shradha Naik | Start building chatbot early in the project | Stop adding features without prompt validation | Continue modular design | Stabilized chatbot core functionality
2 | 2 | 2025-11-05 | 2025-11-12 | Shradha Naik | Start validating contracts before analysis | Stop manual compliance checks | Continue structured reporting | Improved compliance accuracy
3 | 3 | 2025-11-13 | 2025-11-26 | Shradha Naik | Start tracking regulation versions | Stop assuming static compliance rules | Continue maintaining changelog | Built regulation impact mapping
4 | 4 | 2025-11-27 | 2025-12-10 | Shradha Naik | Start optimizing chatbot responses | Stop static prompt usage | Continue UI testing | Integrated RAG-based chatbot refinement